## SOW
Project Name
Scope of Work - Network Visioning & Implementation (Example)
| Task | Description | Deliverables
Task 1: Project Management
1.1 | Project Team Meetings | Organize Monthly Project Development Team Meetings | XXX
1.2 | Invoicing and Reporting | Monthly Invoicing and Project Reporting | XXX
Task 2: Technical Development and Existing Conditions
2.1 | Current Network Performance Assessment | Compile existing collision, traffic, and speed data, demographics of walking and biking, land use and key destinations, existing mode share, level of traffic stress analysis, level of comfort, air quality, active transportation counts, short trips analysis, and business performance to establish a baseline. | XXX
2.2 | Modeling | Model project benefits through conversion of short trips to active transportation, trips in built-out network, and LOS analysis. | XXX
| Complete Network Mapping | Based on technical analysis, develop a series of maps for full network build out including corridors, type of facility, land use and key destinations and level of comfort.
Task 3: Community Engagement
3.1 | Engagement Plan | Develop a community engagement plan including number of community touch points, advertising and marketing strategies. Strategies should consider low-tech and virtual options due to impacts from COVID-19. | XXX
3.2 | Community Workshops | Host a minimum of three pop-up workshops throughout the community with interactive and creative input/feedback to educate the public on the project. | XXX
3.3 | Walk and Bike Audits | Organize a minimum of two community walks and bike rides to collect specific community input and educate the public on the project. | XXX
3.4 | Community Advisory Committee Formation | Convene community advisory committee comprised of local stakeholders and community members to serve as a project steering committee. | XXX
Task 4: Quick Build Pilot Project Plans and Materials
4.1 | Quick Build project phasing | Develop phasing and implementation plan to implement the most "stressful" segment of the network first as a quick build project. | XXX
4.2 | PS&E Package | Compile conceptual design plans, signage and striping plans, traffic management plans, and cost estimates, reviewed and signed by a licensed Professional Eningeer (P.E.). Obtain and pay for necessary permits. | XXX
4.2 | Materials Plan and Budget | Develop a materials and sourcing plan including cost per unit of each material and plan for maintaining secure storage of the materials. | XXX
Task 5: Implementation and Evaluation
5.1 | Evaluation and Documentation Strategy | Develop and implement a documentation strategy that includes before/after count data, audit data, existing conditions, projected use, economic analysis, photography and videography. Includes media coverage, community input on proposed changes in street design, intercept surveys and analysis in targeted locations to determine the effect and benefit of the project. | XXX
5.2 | Project Implementation and Monitoring | Develop and implement a maintenance and monitoring plan throughout the life of the project. Working with a contractor, implement the project including traffic management, staging, striping, removal of materials, and oversight. | XXX
Task 6: Final Reports and Presentations
6.1 | Draft Final Report | Develop a final report that summarizes the project, feedback and data collected, and includes next steps and recommendations | XXX
6.2 | Final Report and Presentations | Final report documenting all aspects of the project. Presentation to City Council and/or Commission. | XXX

## TIMELINE
PROJECT TIMELINE
| Project Title | YOUR PROJECT NAME HERE
Task Number | Task Title | Months after NTP
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1
1.1
1.2
1.3
2
2.1
2.2
2.3
2.4
2.5
2.6
3
3.1
3.2
3.3
3.4
3.5
3.6
4
4.1
4.2
4.3
4.4
4.5
5
5.1
5.2
5.3
6
6.1
6.2
6.3

## BUDGET
LINE ITEM BUDGET:
Project Name
Complete the fields with blue text only
Use a fully-burdened hourly rate that incorporates fringe and overhead.
Warning! If you add or delete any columns make sure all formulas are still functioning to give correct totals.
(a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p)
Cost Categories | Fully-Burdened Hourly Rate | Task 1 |  | Task 2 |  | Task 3 |  | Task 4 |  | Task 5 |  | Task 6 |  | Grand Total (All tasks)
|  | XXX |  | XXX |  | XXX |  | XXX |  | XXX |  | XXX
|  | Hours | Amount | Hours | Amount | Hours | Amount | Hours | Amount | Hours | Amount | Hours | Amount | Hours | Amount
Direct Labor Classification(s):
Principal-in-Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Senior Engineer (P.E.) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Manager | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sr. Planner/Modeler | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Intermediate Planner/Modeler | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add additional as needed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Direct Labor |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs ( ODCs)
Travel |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Printing - Directly Chargeable only |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Social Media |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Programming Activities |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Project Materials |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Traffic Management |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Subtotal - ODCs: |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Subconsultant(s)*
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Subconsultant(s): |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GRAND TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0